## Sheet1
Week | Project: Flask ML Webapp Service | Estimated Normal (hours) | Estimated Best (hours) | Estimated Worst (hours) | Description
2020-10-01 | Project Planning | 3 | 2 | 5 | weekly plan, Trello board, set up github repository
2020-10-08 | local code implementation | 10 | 8 | 12 | implement python codes
2020-10-15 | Prepare Makefile | 2 | 1 | 3 | write Makefile
2020-10-22 | Set up ADO Cloud DevOps for the project | 5 | 4 | 6 | create CI/CD pipelines
2020-10-29 | Deploy the webapp service in Azure | 2 | 1 | 3 | create webapp services on the cloud, deploy initial versions
2020-11-05 | Set up monitoring tools | 3 | 2 | 4 | monitor webapp logs
2020-11-12 | Demo | 2 | 2 | 3 | show demo to customers
2020-11-19 | Add new features | TBD | TBD | TBD | add new features proposed by the team
2020-11-26 | Deploy into production | 3 | 2 | 4 | smoke test and deploy
2020-12-03 | Start maintenance | TBD | TBD | TBD | get feedback
| Goals | Goals
Deploy a Python-based machine learning webapp in production
Complete CI/CD from code to delivery
Codes are always tested before deployment